## Frame Installation Tracker
Middlesex – Frame Installation Tracker
Source: Colfab schedule • Graboyes installation tracking • Generated 05/22/2026
COLFAB SCHEDULE (reference) | [8 empty] | GRABOYES INSTALLATION TRACKING (fill in)
Line # | Area | Location | Floor | Frame Type | Qty | Colfab Status | Delivery Date | Colfab Notes | Shipment Received | Install Started | Install Completed | Days to Install | Graboyes Notes
1 | D | Press | 3rd | CW-A | 4 | In Production | 2026-05-15
2 | D | Press | 3rd | CW-B1 | 6 | In Production | 2026-05-18
3 | D | Press | 3rd | CW-C1 | 1 | In Production | 2026-05-18
4 | D | Press | 3rd | CW-F | 1 | In Production | 2026-05-18
5 | D | Press | 3rd | SF-F | 1 | Delivered | 2026-05-11 | Without Door Frames
6 | D | Press | 3rd | SF-E | 1 | Complete | 2026-05-14 | Without Door Frames
7 | D | Press | 3rd | SF-H | 1 | Not by Colfab | N/A | Door Only
8 | C | Press | 3rd | CW-B1 | 3 | In Production | 2026-05-20
9 | C | Press | 3rd | CW-B2 | 2 | In Production | 2026-05-20
10 | C | Press | 3rd | CW-B3 | 1 | In Production | 2026-05-20
11 | C | Press | 3rd | CW-C | 1 | In Production | 2026-05-22
12 | C | Press | 3rd | CW-A | 5 | In Production | 2026-05-22
13 | C | Press | 3rd | CW-E2 | 1 | In Production | 2026-05-27
14 | C | Press | 3rd | CW-E1 | 1 | In Production | 2026-05-27
15 | C | Press | 3rd | CW-D | 1 | In Production | 2026-05-29
16 | C | Concourse | 2nd | SF-C3 | 1 | Complete | 2026-05-14 | Without Door Frames
17 | C | Concourse | 2nd | SF-C2 | 1 | Complete | 2026-05-14 | Without Door Frames
18 | C | Concourse | 2nd | SF-C1 | 1 | Complete | 2026-05-14 | Without Door Frames
19 | C | Ground | Ground | SF-I | 1 | Not by Colfab | N/A | Door Only
20 | C | Ground | Ground | SF-G | 1 | Not by Colfab | N/A | Door Only
21 | B | Press | 3rd | CW-B1 | 9 | In Production | 2026-06-03
22 | B | Press | 3rd | SF-D3 | 1 | Complete | 2026-05-14 | Without Door Frames
23 | B | Press | 3rd | SF-D2 | 3 | Complete | 2026-05-14 | Without Door Frames
24 | B | Press | 3rd | SF-D1 | 1 | Complete | 2026-05-14 | Without Door Frames
25 | B | Concourse | 2nd | SF-B | 1 | In Production | 2026-06-05
26 | A | Concourse | 2nd | CW-A | 6 | In Production | 2026-06-08
27 | A | Concourse | 2nd | CW-B1 | 2 | In Production | 2026-06-08
28 | A | Concourse | 2nd | SF-A | 1 | In Production | 2026-06-08
29 | A | Gateway | Gateway | CW-K | 2 | In Production | 2026-06-10
30 | A | Gateway | Gateway | CW-L | 2 | In Production | 2026-06-10
31 | A | Gateway | Gateway | CW-G | 1 | In Production | 2026-06-10
32 | A | Gateway | Gateway | CW-J | 1 | In Production | 2026-06-12
33 | A | Gateway | Gateway | CW-H | 1 | In Production | 2026-06-12
34 | A | Gateway | Gateway | CW-I | 1 | In Production | 2026-06-12
SUMMARY |  |  |  |  | LEGEND
Total Lines: | 34 |  |  |  |  | Delivered (Colfab)
Total Frames (Qty): | 67 |  |  |  |  | Complete (Colfab)
Shipments Received: | 0 |  |  |  |  | Not by Colfab
Installs Started: | 0 |  |  |  |  | Past delivery, not received
Installs Completed: | 0 |  |  |  |  | Install completed
% Complete: | 0% |  |  |  |  | Graboyes input cell
Avg Days to Install:
INSTRUCTIONS FOR GRABOYES STAFF
1. When a shipment of frames arrives on-site, enter the date received in column J for each line item in that shipment.
2. When installation begins for a line/frame type, enter the start date in column K.
3. When installation is fully complete for that line, enter the completion date in column L.
4. Column M (Days to Install) auto-calculates once both K and L are filled in.
5. Use column N for any field notes (damaged frames, punch-list items, delays, etc.).
6. Yellow-highlighted cells are the ONLY cells that need to be edited. All other columns are reference data from Colfab.

## Panel Counts
Panel Counts by Drawing — Cassettes by Area
Source: 'Cassettes by Area_Middlesex.pdf' (sheets 201–208). NOTE: drawing IDs (CW-1…CW-11) do not match Frame Tracker codes (CW-A, CW-B1, etc.). Use this sheet as reference only.
Drawing | Sheet # | Cassette QTY (THUS) | Glass Panels / Cassette | Doors / Cassette | Total Items / Cassette | Total Items (× QTY) | Notes | Qty Fabricated | Date Shipped to Jobsite | Date Installed at Jobsite
CW-1 | 201 | 1 | 15 | 2 | 17 | 17 | Full-height clearwall. 5 angled clerestory + 5 middle + 5 bottom (incl. 1 transom above door pair X100A). 14 fixed glass + 1 transom + 1 door pair.
CW-2 | 202 | 1 | 12 | 0 | 12 | 12 | Long horizontal clearwall split across match line. 5 panels top section + 7 panels bottom section. All GLA-01A. No doors.
CW-3 | 203 | 10 | 1 | 0 | 1 | 10 | Single-panel cassette, GLA-01A. Built 10 times. 10 cassettes × 1 panel = 10 panels total.
CW-4 | 203 | 1 | 1 | 0 | 1 | 1 | Single-panel cassette, GLA-01A.
CW-5 | 203 | 1 | 1 | 0 | 1 | 1 | Single-panel cassette, GLA-01A.
CW-6 | 204 | 1 | 15 | 2 | 17 | 17 | Mirror of CW-1. Door pair X100B in bottom row. 14 fixed glass + 1 transom + 1 door pair.
CW-7 | 205 | 1 | 24 | 4 | 28 | 28 | Two-section clearwall with match line. Top section ~11 glass + 2 single doors (X120D, X120C). Bottom section ~13 glass + 2 single doors (X120B, X120A). VERIFY count against drawing — complex elevation.
CW-8 | 206 | 1 | 1 | 0 | 1 | 1 | Single-panel cassette, GLA-01A.
CW-9 | 206 | 1 | 3 | 0 | 3 | 3 | Three-panel angled clearwall. All GLA-01.
CW-10 | 207 | 1 | 12 | 2 | 14 | 14 | Two-section clearwall. Top section 6 glass + 1 single door (X210A). Bottom section 5 glass + 1 single door (X210B) + transoms.
CW-11 | 208 | 1 | 3 | 0 | 3 | 3 | Three-panel angled clearwall. All GLA-01.
TOTAL |  | 20 | 88 | 10 | 98 | 107 |  | 0
DEFINITIONS
Cassette QTY (THUS): |  | The number of times this elevation gets built — taken from the '(N) THUS' callout in each drawing's title block.
Glass Panels / Cassette: |  | Number of fixed glass panels (GLA-xx labels) in one elevation. Transoms above doors are counted.
Doors / Cassette: |  | Number of individual door leaves in one elevation. Door pairs count as 2.
Total Items / Cassette: |  | Glass + doors per cassette (auto-calculated).
Total Items (× QTY): |  | Cassette QTY × items per cassette — the field count Graboyes should expect to install across all instances of that drawing.
Highlighted row (CW-7): |  | Complex two-section elevation with 4 doors. Counts are best-effort; verify against drawing before ordering or installation.
IMPORTANT — NAMING MISMATCH WITH FRAME TRACKER
The drawings in 'Cassettes by Area_Middlesex.pdf' use clearwall IDs CW-1 through CW-11. The Frame Tracker sheet uses different IDs (CW-A, CW-B1, CW-B2, CW-C, CW-C1, CW-D, CW-E1, CW-E2, CW-F, CW-G, CW-H, CW-I, CW-J, CW-K, CW-L). No mapping was provided between the two systems and none could be inferred from the drawings. Storefront types (SF-A through SF-I) are not in the uploaded drawing set and are not represented on this sheet. Before tying panel counts to specific schedule line items, obtain the elevation index / key from the architect (AECOM) or Colfab that maps drawing IDs to Frame Tracker codes.
Note on I3: Ellis Guiles: Enter Qty Fabricated as a running cumulative total: each day, add the current day's fabricated quantity to the previous day's total. Continue updating daily until 100% of the Qty (column C) is reached.